## Commercial_2026
S. No | Risk Description | Inherent Risk Level | Current Mitigation | Current | Risk Owner | Risk Treatment |  |  | Net
Risk Level
|  | (Impact/ Likelihood) |  | (Impact/ Likelihood) |  |  |  |  | Risk Level
[6 empty] | Action Plan | Due Date | Action owner | (Impact/ Likelihood)
1 | Adverse variations in production profile leading to reduced availability of gas to transport from planned sources | HIGH I - Extreme L - Possible | a. Alternative potential sources of gas and terminals evaluation for market / source expansion on periodic basis b. Connectivity with CGD entities commissioned for connection - to augment supplies from the west c. Unified tariff implemented under PNGRB regulations makes transportation of gas from different sources become viable agnostic of source and distance & improves commercial viability for transportation using PIL Network.CGD sector is being charged Zone 1 unified tariff for CNG / PNG-D volumes which will help in accelerated growth of the sector. d. PNGRB is likely to invite bids for a new pipeline from Ennore LNG terminal to Kondapalli terminating at PIL pipeline which has the potential for incremental volume from Ennore terminal. | MEDIUM I - Major L - Unlikely | Mahesh / Mohit | a) Undertake periodic demand survey along pipeline for identification of potential customers for connectivity in 3 years (b) Enter into MoU with potential new sources for commercial and technical feasibility studies for connectivity. - | a. FY 2029 b. Ongoing | Mohit
2 | Temporary outage of sources/ terminals/ connected customers leading to reduced volumes | Medium I - Minor (assumption ~10 days worth volume impacted) L - Probable | a. Use of imbalance management services / operational arrangement with connected transporters/customer for ensuring continuity of transportation/ supply b. Business Interruption Clause in Mega policy (Extension) c. Contractual flexibility, protecting commercial interest of PIL | LOW I - Minor L - Possible | Mahesh / Mohit
3 | Extended (Long term) outage of key sources - KGD6 | HIGH I - Extreme L - Unlikely | a. Contracted capacity payments under PUA b. Business Interruption Clause in Mega policy (Extension) c. Alternative sources from west coast to meet RFCL as well as east coast customers and CGD sector customers which are directly connected to PIL pipeline. | MEDIUM I - Major L - Unlikely | Manoj
4 | Extended (Long term) outage due to pipeline failure leading to inability to serve customer | HIGH I - Extreme L - Unlikely | a. Operational arrangement with interconnected transporter(s) for supply of gas to customer by swapping of Gas, to the extent of operational feasibility b. Corrective maintenance readiness as per BCP plan c. Business Interruption Clause in Mega policy (Extension) | MEDIUM I - Major L - Unlikely | Mahesh/ Mohit
5 | Reduced gas availability from or delays in upstream projects (under development) leading to reduced gas flows | HIGH I - Extreme L - Unlikely | a. Continuous engagement with upstream parties to monitor progress for ongoing projects b. ONGC, Mallavaram volume as per plan expected by Q4 FY 27 c. Seek connectivity with new and existing R-LNG terminals as well as cross country pipelines for tapping new sources of gas and customers d. PNGRB is likely to invite bids for a new pipeline from Ennore LNG terminal to to Kondapalli terminating at PIL Pipeline (TOP-1 ) which has the potential to provide incremental volumes in PIL pipeline upon connection to PIL pipeline. | MEDIUM I - Major L - Unlikely | Manoj
6 | Revenues Dependability on limited customers (RIL and GSPL for significant volumes), varying customer preference(s); Customers inability/ willingness to offtake Gas | MINIMAL I - Negligible L - Possible | a. Continuously evaluate increase in customer base - Tie up with new customers. 15 new connections commissioned b. Periodic demand Survey study to assess potential gas sources and customer footprint c. Pursue connectivity optionsalong PIL pipeline d. Unified tariff implemented under PNGRB regulations makes transportation of gas agnostic of source and distance & improves commercial viability for transportation using PIL Network. CGD sector is being charged Zone 1 unified tariff for CNG / PNG-D volumes which will help in accelerated growth of the sector. e. Periodic updating of customers demand to ensure flexibility of diversion of volumes in case of temporary failure of a single customer. f. Parking facility for temporary storage of gas is being offered g. Business Interuption Clause in Mega policy (Extension) h. New large volume customers like IOCL and GAIL have been onboarded as well. | MINIMAL I - Negligible L - Possible | Mahesh/ Mohit
7 | Project execution delays at PIL leading to delay in physical connectivity to new sources/ customers resulting in inability to tap into new markets (ONGC and CGD )connectivity) | LOW I- Minor L- Possible | a. Periodic monitoring of project status through Project review committee b. Management intervention for expedition on need basis e.g. insource versus outsource | LOW I- Minor L- Possible | Mahesh/ Mohit | Monthly review of ongoing projects with technical/project team | Ongoing | Mahesh Shedbal/ Mohit
8 | Competition from alternate fuels (i) at customer level - LNG, LPG, FO (ii) at industry level - Power sector, competition from renewables | LOW I- Minor L- Possible | a. Implementation of Unified tariff has made transportation source / distance agnostic and thereby reducing the cost for customers to make gas competitive with other fuels. b. Policy advocacy for usage of natural gas as a clean energy source c. Periodic Customer engagement for promoting natural gas usages | LOW I- Minor L- Possible | Neeraj / Mohit
9 | Shipper’s payment default leading to postponement of cash flow/ litigation | LOW I- Minor L- Possible | a. Ensuring adequate payment security - LC/ advance/ Security deposit prior to starting service(s) b. Monitoring payment security status and initiating mitigation actions c. Contractual clauses for levy of penal interest on delayed payment | MINIMAL I - Negligible L - Possible | Mahesh Shedbal | LC module for monitoring payment security is being developed | 2026-06-30 | Mahesh shedbal
10 | Adverse Regulatory Amendments / Policy changes including tariff revision by PNGRB on account of unfavorable assessment leading to lower revenue | HIGH I - Major L - Possible | a. Regular engagements and Policy Advocacy with PNGRB and MOPNG, also through industry bodies b. PNGRB has revised PIL tariff upward in December 2025 to be effective from 01.01.2026 which is a positive development.Regular Tariff revision proposal as per Tariff regulation approved by PNGRB c. Capacity assessment matter, APTEL -Tribunal has directed PNGRB to complete assessment in a timebound manner& consider PIL’s submission. PNGRB has filed appeal in Supreme Court challenging APTEL order in capacity matter. PIL will pursue the matter for resolution. If APTEL order is upheld in Supreme Court, same is expected to have further positive impact on PIL tariff. | HIGH I - Major L - Possible | Manoj Pandey
11 | Lack of payment security and adverse tax implications | MEDIUM I - Moderate L - Possible | Proposed Actin Plan (May be put as future actions): 1. Incorporation of suitable payment security provisions under Revenue Settlement Mechanism which is to be finalised among transporters in next two months time as per notified regulations. 2. Advocacy with PNGRB and also through industry bodies to get suitable clarification from GoI for availment of Input Tax Credit / other aspects. In case of residual tax implications, regulatory provisions for inclusion of same in formulation of Unfieid Tariff to ensure revenue neutrality for transportation entities. | MEDIUM I - Moderate L - Possible | EVS Rao | Effective date for commencement of regulation is expected to be notified by PNGRB only after finalisation of Revenue Settlement Mechanism and after presence of necessary quorum in PNGRB Board (Currently there is only one Board Member is in place). As part of the settlement committee, PIL has already taken up payment security and GST issues. Efforts will be made to ensure the protection of PIL interest in developing settlement mechanism. Regulation in place.
12 | Failure of PGTS system leading to disruption in daily business operations | MINIMAL I - Negligible L -Unlikely | a. Daily back-up in secondary server b. Disaster Recovery server at Hyderabad - Daily incremental back-up c. Timely updation of firewalls and Anti-virus d. 24x7 Security Operation Centre monitoring e. Manual programme available for uploading of invocie ready data in SAP f. Business SOP have defined process for managing business process manually | MINIMAL I - Negligible L -Unlikely | Raghavan / Ganesh Borse

## Commercial-23.02.26
S. No | Risk Description | Inherent Risk Level | Current Mitigation | Current | Risk Owner | Risk Treatment |  |  | Net
Risk Level
|  | (Impact/ Likelihood) |  | (Impact/ Likelihood) |  |  |  |  | Risk Level
[6 empty] | Action Plan | Due Date | Action owner | (Impact/ Likelihood)
1 | Adverse variations in production profile leading to reduced availability of gas to transport from planned sources | HIGH | a. Alternative potential sources of gas and terminals to be evaluated for connectivity for market / source expansion from time to time. | MEDIUM | Mahesh / Mohit | (a) Undertake periodic demand survey along pipeline for identification of potential customers for connectivity. | Ongoing
|  | I - Extreme | b. Connectivity with CGD entities commissioned for connection - to augment supplies from the west | I - Major |  | (b) Enter into MoU with potential new sources for commercial and technical feasibility studies for connectivity.
|  | L - Possible | c. Unified tariff implemented under PNGRB regulations which makes transportation of gas agnostic of source and distance & improves commercial viability for transportation using PIL Network. CGD sector is being charged Zone 1 unified tariff for CNG / PNG-D volumes which will help in accelerated growth of the sector. | L - Unlikely
d. PNGRB is likely to invited bids for a new pipeline from Ennore LNG terminal to Kondapalli terminating at PIL pipeline which has the potential for incremental volume from Ennore terminal.
2 | Temporary outage of sources/ terminals/ connected customers leading to reduced volumes | Medium | a. Use of imbalance management services / operational arrangement with connected transporters/customer for ensuring continuity of transportation/ supply | LOW | Mahesh / Mohit
|  | I - Minor (assumption ~10 days worth volume impacted) | b. Business Interruption Clause in Mega policy (Extension) | I - Minor
|  | L - Probable | c. Contractual flexibility, protecting commercial interest of PIL | L - Possible
3 | Extended (Long term) outage of key sources - KGD6 | HIGH | a. Contracted capacity payments under PUA | MEDIUM | Manoj
|  | I - Extreme | b. Business Interruption Clause in Mega policy (Extension) | I - Major
|  | L - Unlikely | c. Alternative sources from west coast to meet RFCL as well as east coast customers and CGD sector customers which are directly connected to PIL pipeline. | L - Unlikely
4 | Extended (Long term) outage due to pipeline failure leading to inability to serve customer | HIGH | a. Operational arrangement with interconnected transporter(s) for supply of gas to customer by swapping of Gas, to the extent of operational feasibility | MEDIUM | Mahesh / Mohit
|  | I - Extreme | b. Corrective maintenance readiness as per BCP plan | I - Major
|  | L - Unlikely | c. Business Interruption Clause in Mega policy (Extension) | L - Unlikely
5 | Reduced gas availability from or delays in upstream projects (under development) leading to reduced gas flows | HIGH | a. Continuous engagement with upstream parties to monitor progress for ongoing projects | MEDIUM | Manoj
|  | I - Extreme | b. Seek connectivity with new and existing R-LNG terminals as well as cross country pipelines for tapping new sources of gas and customers. | I - Major
|  | L - Unlikely | d. PNGRB is likely to invite bids for a new pipeline from Ennore LNG terminal to Kondapalli terminating at PIL Pipeline which has the potential to provide incremental volumes in PIL pipeline upon connection to PIL pipeline. | L - Unlikely
6 | Revenues Dependability on limited customers (RIL and GSPL for significant volumes), varying customer preference(s); Customers inability/ willingness to offtake Gas | MINIMAL | a. Continuously evaluate increase in customer base - Tie up with new customers. 15 new connections commissioned and commissioned | MINIMAL | Mahesh/ Mohit
|  | I - Negligible | b. Undertake periodic demand Survey study to assess potential gas sources and customer footprint. | I - Negligible
|  | L - Possible | c. Pursue connectivity options along PIL pipeline | L - Possible
d. Unified tariff implemented under PNGRB regulations which makes transportation of gas agnostic of source and distance & improves commercial viability for transportation using PIL Network. CGD sector is being charged Zone 1 unified tariff for CNG / PNG-D volumes which will help in accelerated growth of the sector.
e. Periodic updating of customers demand to ensure flexibility of diversion of volumes in case of temporary failure of a single customer.
f. Parking facility for temporary storage of gas is being offered
g. Business Interuption Clause in Mega policy (Extension)
h. New large volume customers like IOCL and GAIL have been onboarded as well.
7 | Project execution delays at PIL leading to delay in physical connectivity to new sources/ customers resulting in inability to tap into new markets | LOW | a. Periodic monitoring of project status through Project review committee | LOW | Mahesh/ Mohit | Monthly review of ongoing projects with technical/project team | Ongoing | Mahesh / Mohit
| (ONGC and CGD connectivity) | I - Minor | b. Management intervention for expedition on need basis e.g. insource versus outsource | I - Minor
|  | L - Possible |  | L - Possible
8 | Competition from alternate fuels (i) at customer level - LNG, LPG, FO (ii) at industry level - Power sector, competition from renewables | LOW | a. Implementation of Unified tariff has made transportation source / distance agnostic and thereby reducing the cost for customers to make gas competitive with other fuels. | LOW | Neeraj / Mohit
|  | I - Minor | b. Policy advocacy for usage of natural gas as a clean energy source | I - Minor
|  | L - Possible | Periodic Customer engagement for promoting natural gas usages | L - Possible
9 | Shipper’s payment default leading to postponement of cash flow/ litigation | LOW | a. Ensuring adequate payment security - LC/ advance/ Security deposit prior to starting service(s) | MINIMAL | Mahesh | LC module for monitoring payment security is being developed | on going
|  | I - Minor | b. Monitoring payment security status and initiating mitigation actions | I - Negligible
|  | L - Possible | c. Contractual clauses for levy of penal interest on delayed payment | L - Possible
10 | Adverse Regulatory Amendments / Policy changes including tariff revision by PNGRB on account of unfavorable assessment leading to lower revenue | HIGH I - Major L - Possible | a. PNGRB has revised PIL tariff upward in December 2025 to be effective from 01.01.2026 which is a positive development. b. In the capacity assessment matter, APTEL -Tribunal has directed PNGRB to complete assessment in a timebound manner& consider PIL’s submission. PNGRB has filed appeal in Supreme Court challenging APTEL order in capacity matter. PIL will pursue the matter for resolution. If APTEL order is upheld in Supreme Court, same is expected to have further positive impact on PIL tariff. c. For reforms in regulations, PIL will continue regular engagements and Policy Advocacy with PNGRB and MOPNG, also through industry bodies. | HIGH I - Major L - Possible | Manoj
11 | Lack of payment security and adverse tax implications | MEDIUM I - Moderate L - Possible | Proposed Actin Plan (May be put as future actions): 1. Incorporation of suitable payment security provisions under Revenue Settlement Mechanism which is to be finalised among transporters in next two months time as per notified regulations. 2. Advocacy with PNGRB and also through industry bodies to get suitable clarification from GoI for availment of Input Tax Credit / other aspects. In case of residual tax implications, regulatory provisions for inclusion of same in formulation of Unfieid Tariff to ensure revenue neutrality for transportation entities. | MEDIUM I - Moderate L - Possible | EVS Rao | Effective date for commencement of regulation is expected to be notified by PNGRB only after finalisation of Revenue Settlement Mechanism and after presence of necessary quorum in PNGRB Board (Currently there is only one Board Member is in place). As part of the settlement committee, PIL has already taken up payment security and GST issues. Efforts will be made to ensure the protection of PIL interest in developing settlement mechanism. |  |  |  | Can be moved in risk no 10
11 | Failure of PGTS system leading to disruption in daily business operations | MINIMAL | a. Daily back-up in secondary server | MINIMAL | Raghavan / Ganesh Borse
|  | I - Negligible | b. Disaster Recovery server at Hyderabad - Daily incremental back-up | I - Negligible
|  | L -Unlikely | c. Timely updation of firewalls and Anti-virus | L -Unlikely
d. 24x7 Security Operation Centre monitoring
e. Manual programme available for uploading of invocie ready data in SAP
f. Business SOP have defined process for managing business process manually